## Slide 1: CASA-1000 TAP - 500 Afghanistan’s Energy Connectivity ,Central to South Asia

## Slide 2: CASA-1000 Afghanistan’s First Energy Connectivity Initiative Project Status and Progress

## Slide 3: Purpose
Political SCOPE: CASA-1000 is an Economic Project that will transform the political and security landscape of the region.
Economic Scope: It will bound South and Central Asia in trade and economic ties and is intended to significantly improve the economies of the two region, by reducing energy deficit of Pakistan to accelerate industrial productivity, and by providing a better market for surplus energy of Central Asian countries.
Technical Scope: 1000 MW Electricity will be transferred to Pakistan over a 500kV DC line that will start from Sangtuda of Tajikistan and End in Nowshehra of Pakistan, over a period of 15years from the date of commissioning, with Two HVDC Converter Stations at both ends.

## Slide 4: Cost and Funding Agencies?
Cost:
Total Eligible Cost of the Project is expected at around $1bn
Funding Agencies: International Finance Institutions such as WB, ISDB, EIB
Also
USAID and DFID etc

## Slide 5: Project Design And Procurement Status
Converter Stations for HVDC Line in Tajikistan and Pakistan | HVDC Line in Afghanistan | HVDC Line in Pakistan | HVDC Line in Tajikistan | HVAC Line in Tajikistan | HVAC Line in Kyrgyzstan
Financial Bids Opened | Contracts Awarded | Bidding Announcement (by mid April) | Notice of Award Stage | Technical evaluation Completed | Technical Evaluation Completed
All procurement planned to be closed by End of August, and Construction Begins Late 2018.

## Slide 6: Completion and Operation?
Commissioning of Line and converter stations:
42 Months after effectiveness of Construction, Probably by early 2022
Operations:
15 Years after commissioning. Can be extended if agreed by all parties.

## Slide 7: Legal and Commercial Frameworks
1. Master Agreement
2. Foundational Power Purchase Agreement
3. Bilateral Power Purchase Agreements between buyers and sellers
3. Host Government Agreements
4. Coordination Agreements between Sellers-Sellers
5. Finance Agreement between governments and funding agencies
6. Subsidiary Loan Agreement between Government and National Electricity Utilities
All legal, Commercial and country specific implementation arrangements have been signed

## Slide 8: Organization and Administrative Structure
Inter Ministerial Government Council: Highest forum of decision making and strategic steering of the project
Joint Working Group: Deputy Ministerial Level Technical and Policy Recommendation Forum.
Procurement Committee: on Par with JWG, an authorized decision making body on procurement issues.
Other committees that existed in the past: finance Committee, Legal Sub-committee

## Slide 9: Organization and Administration…
Project Secretariat: Headquartered in Almaty. This is IGC secretariat that conducts affairs on behalf of countries and make recommendations to countries.
IFC: A procurement wing of IGC, lead all procurement related issues such as Procurement of EPC Contractors.

## Slide 10: Next Steps
1. Close procurement stage by Mid August
2. . Re-orient the project secretariat into an Operating Committee after completion of procurement stage and beginning of Construction Phase.

## Slide 11: TAP-500 Turkmenistan ,Afghanistan and Pakistan Energy Connectivity Project Status and Progress

## Slide 12: TAP – 500KV
Mary Turkmenistan to Herat – Kandahar Afghanistan to Quetta Pakistan
Approximately 2000MW Capacity
MoU sign on 13 Dec 2015
The Intergovernmental Agreement sign on 23 Feb 2018
1st Ministerial meeting on 29 – 30 Mar 2018 Ashgabat
    Agreed to create a TWG (Technical Working Group)
    1st TWG meeting will hold end of April in Islamabad Pakistan

## Slide 13: !?